## Dashboard
DASHBOARD
Effort Consumption over time
FINANCIAL SUMMARY
Actual Vs Budget
EFFORT CONSUMPTION
Consumed Vs Planned

## Financial Estimates
FINANCIAL ESTIMATION
Sl NO	FIXED COSTS	INR	USD
1			.00
2			.00
3			.00
A	TOTAL FIXED COSTS		.00
Sl NO	OPTIONAL COSTS	INR	USD
4			.00
B	TOTAL OPTIONAL COSTS		.00
Sl NO	RECURRING COSTS	INR	USD
5			.00
6			.00
7			.00
8			.00

C	TOTAL RECURRING COSTS		0
	TOTAL (A + B + C)		.00

	CONTRACTED COST		1,351.00
	ESTIMATED COST		.00
	ACTUAL COST

	ESTIMATED EFFORT		15
	ACTUAL EFFORT		0

## Tasks
Tasks
id	Task	Duration in days	Start	Finish	Actual Start	Actual Finish	Actual Effort	Cumulative Estimated Effort	Cumulative Actual Effort
	AB Suite API Implementation		1 Nov 19	14 May 20
	Project hand-over from Sales to delivery Team	0.25	1 Nov 19	1 Nov 19			0	0.25	0
	Pre Kick-off activities	0.25	1 Nov 19	1 Nov 19			0	0.5	0
	Create project on Bugzilla	0.25	1 Nov 19	1 Nov 19			0	0.75	0
	Create project on Zoho desk	0.25	1 Nov 19	1 Nov 19			0	1	0
	Create Project on Zoho Cliq	0.25	1 Nov 19	1 Nov 19			0	1.25	0
	Create project group on Zoho Mail	0.25	1 Nov 19	1 Nov 19			0	1.5	0
	Create Project on GIT repository	0.25	1 Nov 19	1 Nov 19			0	1.75	0
	Circulate Discovery document to the stakeholders	0.25	1 Nov 19	1 Nov 19			0	2	0
	Update this schedule with resource names	0.25	1 Nov 19	1 Nov 19			0	2.25	0
	Project Kick-off	0.25	1 Nov 19	4 Nov 19			0	2.5	0
	Creating and Setting up Infrastructure	0.25	4 Nov 19	11 Nov 19			0	2.75	0
	Spinning a new instance of the VPS	0.25	4 Nov 19	4 Nov 19			0	3	0
	Install VPS Infrastructure	0.25	4 Nov 19	4 Nov 19			0	3.25	0
	Creating Users who will have root access	0.25	4 Nov 19	4 Nov 19			0	3.5	0
	Set up IP Tables	0.25	4 Nov 19	5 Nov 19			0	3.75	0
	Harden the VPS		5 Nov 19	5 Nov 19				3.75	0
	Install Technology Stack - Database - MySQL Installation	0.25	5 Nov 19	6 Nov 19			0	4	0
	Install Technology Stack - Webserver - NGINX Installation	0.25	6 Nov 19	6 Nov 19			0	4.25	0
	Install Technology Stack – API Infrastructure Installation	0.25	6 Nov 19	8 Nov 19			0	4.5	0
	Install the AB API Components	0.25	6 Nov 19	7 Nov 19			0	4.75	0
	Install the AB UI Components	0.25	8 Nov 19	11 Nov 19			0	5	0
	Configure the System wide entitlements (use the API's to upload)	0.25	11 Nov 19	13 Nov 19			0	5.25	0
	Create Roles	0.25	11 Nov 19	12 Nov 19			0	5.5	0
	Create Users	0.25	11 Nov 19	12 Nov 19			0	5.75	0
	Setup access and entitlements in the application	0.25	12 Nov 19	12 Nov 19			0	6	0
	Setup configure.js	0.25	11 Nov 19	12 Nov 19			0	6.25	0
	Setup Label.js	0.25	12 Nov 19	13 Nov 19			0	6.5	0
	Setup Constant.js	0.25	12 Nov 19	13 Nov 19			0	6.75	0
	Configure the Static Data (use the API's to upload. Use defaults supplied by AB)	0.25	12 Nov 19	14 Nov 19			0	7	0
	Set up Address Types	0.25	12 Nov 19	12 Nov 19			0	7.25	0
	Set up Bank Information	0.25	12 Nov 19	12 Nov 19			0	7.5	0
	Set up salutation	0.25	12 Nov 19	12 Nov 19			0	7.25	0
	Set up Gender	0.25	12 Nov 19	12 Nov 19			0	7.5	0
	Set up Religion	0.25	12 Nov 19	12 Nov 19			0	7.75	0
	Set up the Preferred Language	0.25	12 Nov 19	13 Nov 19			0	8	0
	Set up the Marital Status	0.25	13 Nov 19	13 Nov 19			0	8.25	0
	Set up the education Types	0.25	13 Nov 19	13 Nov 19			0	8.5	0
	Set up the Lead Constitution	0.25	13 Nov 19	13 Nov 19			0	8.75	0
	Set up the Business Type	0.25	12 Nov 19	12 Nov 19				8.75	0
	Set up the collateral	0.25	12 Nov 19	12 Nov 19			0	9	0
	Set up the countries	0.25	12 Nov 19	12 Nov 19			0	9.25	0
	Set up the Currencies	0.25	12 Nov 19	13 Nov 19			0	9.5	0
	Set up the Purpose	0.25	13 Nov 19	13 Nov 19			0	9.75	0
	Set up the School Board	0.25	13 Nov 19	13 Nov 19			0	10	0
	Set up the state	0.25	13 Nov 19	13 Nov 19				10	0
	Set up the Tax Status	0.25	14 Nov 19	14 Nov 19			0	10.25	0
	Configure the negative profiles	0.25	14 Nov 19	14 Nov 19			0	10.5	0
	Set up the credit bureau interfaces	0.25	12 Nov 19	20 Nov 19			0	10.75	0
	Set up the field investigation agencies	0.25	12 Nov 19	14 Nov 19			0	11	0
	Set up KYC and Pre-sanction Documents	0.25	13 Nov 19	18 Nov 19			0	11.25	0
	Configure the Products	0.25	18 Nov 19	20 Dec 19			0	11.5	0
	Set up the Eligibility Criteria		18 Nov 19	26 Nov 19				11.5	0
	Set up Credit Policies	0.25	26 Nov 19	4 Dec 19			0	11.75	0
	Set up scoring	0.25	4 Dec 19	11 Dec 19			0	12	0
	Set up the Products		11 Dec 19	17 Dec 19				12	0
	Set-up Product and Post sanction documents	0.25	17 Dec 19	20 Dec 19			0	12.25	0
	Configure CRM		20 Dec 19	26 Dec 19				12.25	0
	Upload leads atleast one of each constitution	0.25	20 Dec 19	24 Dec 19			0	12.5	0
	Check if all lead forms are working	0.25	24 Dec 19	25 Dec 19			0	12.75	0
	Check Track Leads	0.25	25 Dec 19	26 Dec 19			0	13	0
	Check Lead History	0.25	26 Dec 19	26 Dec 19			0	13.25	0
	Check Search Leads		26 Dec 19	26 Dec 19				13.25	0
	Check Create new Leads	0.25	26 Dec 19	26 Dec 19			0	13.5	0
	Configure ELIGIBITY		26 Dec 19	8 Jan 20				13.5	0
	Check if Credit Bureau interfaces are working	0.25	26 Dec 19	30 Dec 19			0	13.75	0
	Check if facilities interfaces are working (Customisation)	0.25	30 Dec 19	31 Dec 19			0	14	0
	Check if Call Log is working	0.25	31 Dec 19	31 Dec 19			0	14.25	0
	Check if Visit Log is working	0.25	31 Dec 19	1 Jan 20			0	14.5	0
	Check if reassign lead is working	0.25	1 Jan 20	1 Jan 20			0	14.75	0
	Check if Product suggestions are working for all products	0.25	1 Jan 20	7 Jan 20			0	15	0
	Check if the correct KYC documents are being accepted against each product	0.25	7 Jan 20	8 Jan 20			0	15.25	0
	Configure COLE	0.25	8 Jan 20	17 Feb 20			0	15.5	0
	Check if FI cases are being allocated as per capacity	0.25	8 Jan 20	8 Jan 20			0	15.75	0
	Checkif FI results are appearing to the credit team	0.25	8 Jan 20	9 Jan 20			0	16	0
	Check if Dedupe results are appearing to the credit team	0.25	9 Jan 20	9 Jan 20			0	16.25	0
	Check if Eligibility results are appearing to the credit team	0.25	9 Jan 20	10 Jan 20			0	16.5	0
	Check if Credit Policy results are appearing to the credit team	0.25	10 Jan 20	10 Jan 20			0	16.75	0
	Check if Scoring results are appearing to the credit team	0.25	10 Jan 20	10 Jan 20			0	17	0
	Check if Risk assessment results are appearing to the credit team	0.25	10 Jan 20	10 Jan 20			0	17.25	0
	Check if KYC documents are appearing to the credit team	0.25	10 Jan 20	13 Jan 20			0	17.5	0
	Upload Post Sanction documents	0.25	13 Jan 20	14 Jan 20			0	17.75	0
	Generate the CAM report check if all the information is available. Verify if missing info has been entered in previous stages	0.25	14 Jan 20	15 Jan 20			0	18	0
	Check if you loans can be sanctioned for all asset products	0.25	15 Jan 20	20 Jan 20			0	18.25	0
	Check the disbursal Process especially multiple tranche disbursal	0.25	20 Jan 20	24 Jan 20			0	18.5	0
	Generate the repayment structure - Only those repayment struture types configured for th eproduct should be possible	0.25	24 Jan 20	28 Jan 20			0	18.75	0
	Configure Dispatch Welcome kit to be run as a CRON EOD job	0.25	28 Jan 20	28 Jan 20			0	19	0
	Check Send File to Vault especially the status	0.25	28 Jan 20	28 Jan 20			0	19.25	0
	Check the request File from Vault especially the status	0.25	29 Jan 20	29 Jan 20			0	19.5	0
	Check the status when the file is received at vault	0.25	29 Jan 20	29 Jan 20			0	19.75	0
	Request file from Vault	0.25	29 Jan 20	29 Jan 20			0	20	0
	Check the status when the File is dispatched from Vault	0.25	29 Jan 20	30 Jan 20			0	20.25	0
	Configure QR codes to be generated as a CRON EOD	0.25	30 Jan 20	30 Jan 20			0	20.5	0
	Configure Welcome Letters to be generated as CRON EOD	0.25	30 Jan 20	30 Jan 20			0	20.75	0
	Flag Welcome kits as returned	0.25	30 Jan 20	30 Jan 20			0	21	0
	Check the returned Welcome Kits report	0.25	30 Jan 20	31 Jan 20			0	21.25	0
	Receive Incoming Files from the Vault	0.25	31 Jan 20	31 Jan 20			0	21.5	0
	PDC Activities	0.25	31 Jan 20	4 Feb 20			0	21.75	0
	Enter PDC and Security Checks	0.25	31 Jan 20	3 Feb 20			0	22	0
	Send PDC to Vault	0.25	3 Feb 20	3 Feb 20			0	22.25	0
	Swap PDC	0.25	3 Feb 20	4 Feb 20			0	22.5	0
	Vault activities	0.25	4 Feb 20	5 Feb 20			0	22.75	0
	Check if the status is appropriate when the File is sent to vault	0.25	4 Feb 20	4 Feb 20			0	23	0
	Receive the file at vault check the status	0.25	4 Feb 20	4 Feb 20			0	23.25	0
	Check the status when a file is requested from the vault	0.25	4 Feb 20	5 Feb 20			0	23.5	0
	Send the File to OPS and check the status	0.25	5 Feb 20	5 Feb 20			0	23.75	0
	Check the status when the file is received at OPS	0.25	5 Feb 20	5 Feb 20			0	24	0
	Receive PDC's at Vault	0.25	5 Feb 20	5 Feb 20			0	24.25	0
	Repayment	0.25	5 Feb 20	12 Feb 20			0	24.5	0
	Configure the PDC deposit report to run as a CRON EOD	0.25	5 Feb 20	6 Feb 20			0	24.75	0
	Check remove PDC's from deposit	0.25	6 Feb 20	6 Feb 20			0	25	0
	Generate the PDC deposit slip	0.25	6 Feb 20	7 Feb 20			0	25.25	0
	Configure AB to read the Bank statement for cleared PDC's as a CRON EOD	0.25	7 Feb 20	11 Feb 20			0	25.5	0
	Check the Cleared PDC's	0.25	11 Feb 20	11 Feb 20			0	25.75	0
	Flag Bounced PDC's	0.25	11 Feb 20	11 Feb 20			0	26	0
	Check the unrealized instruments report	0.25	11 Feb 20	12 Feb 20			0	26.25	0
	Loan Management	0.25	12 Feb 20	17 Feb 20			0	26.5	0
	Check Loan Cancellation	0.25	12 Feb 20	13 Feb 20			0	26.75	0
	Check Loan Rescheduling	0.25	13 Feb 20	14 Feb 20			0	27	0
	Check Loan Foreclosure	0.25	14 Feb 20	17 Feb 20			0	27.25	0
	Configure CASH	0.25	17 Feb 20	20 Mar 20			0	27.5	0
	Setup the Banks	0.25	17 Feb 20	18 Feb 20			0	27.75	0
	Setup the Chart of Accounts	0.25	18 Feb 20	21 Feb 20			0	28	0
	Setup the Accounting Templates for each event	0.25	21 Feb 20	2 Mar 20			0	28.25	0
	Setup the Charges	0.25	2 Mar 20	4 Mar 20			0	28.5	0
	Verify that the accounting entries are passed for each accounting event in COLE	0.25	4 Mar 20	11 Mar 20			0	28.75	0
	Verify the Trial Balance	0.25	11 Mar 20	16 Mar 20			0	29	0
	Verify the balance Sheet	0.25	16 Mar 20	18 Mar 20			0	29.25	0
	Verify the dashboard figures	0.25	18 Mar 20	20 Mar 20			0	29.5	0
	Configure CAPE	0.25	20 Mar 20	6 Apr 20			0	29.75	0
	Setup the receipt books	0.25	20 Mar 20	23 Mar 20			0	30	0
	Setup the Call Centres and Agents	0.25	23 Mar 20	27 Mar 20			0	30.25	0
	Setup the Collection Agents	0.25	27/03/20 09:30	30/03/20 10:30			0	30.5	0
	Setup the Legal Companies	0.25	30/03/20 10:30	31/03/20 11:30			0	30.75	0
	Setup the DPD rules	0.25	31/03/20 11:30	01/04/20 13:30			0	31	0
	Set up Seucritisation	0.25	01/04/20 13:30	06/04/20 16:30			0	31.25	0
	Configure CARE	0.25	06/04/20 16:30	21/04/20 10:45			0	31.5	0
	Set up CallCentres	0.25	06/04/20 16:30	10/04/20 10:30			0	31.75	0
	Create the team and agents	0.25	10/04/20 10:30	13/04/20 11:30			0	32	0
	Setup the rules	0.25	13/04/20 11:30	16/04/20 15:30			0	32.25	0
	Configure AB to read tickets from Email	0.25	16/04/20 15:30	21/04/20 08:30			0	32.5	0
	Raise a ticket using the form	0.25	21/04/20 08:30	21/04/20 10:45			0	32.75	0
	Customisation	0.25	21/04/20 10:45	14/05/20 09:45			0	33	0
	Integration to Core Banking	0.25	21/04/20 10:45	28/04/20 16:45			0	33.25	0
	Integration to MF registrar	0.25	28/04/20 16:45	06/05/20 13:45			0	33.5	0
	Integration to Insurance Companies	0.25	06/05/20 13:45	14/05/20 09:45			0	33.75	0

## Changes
Bugs and Changes
Id	Description	Reported By	Source	Reported On	Expected Closure Date	Target Release